## Your Name
Log of Hours Worked by Chad Farley
Date | Summary of Tasks Performed |  |  |  | Hours
2014-01-14 | Team meeting. Discussed members strengths and weaknesses. Elected offices for members. Elected as back-end project lead. |  |  |  | 1
2014-01-17 | Began drafting up plans for the basic structure of the backend. Researched different designs and strategies. |  |  |  | 4
2014-01-21 | Team meeting. Shared drafted plans for the backend with the group. Volunteered to oversee the online user manual. |  |  |  | 1
2014-01-23 | Attempted to create a ground dropbox account, no longer had access to business accounts (beta invitation). |  |  |  | 2
2014-01-27 | Team meeting. Proposed software development style. Proposed a locking mechanism for github, will research. Developed email rules. |  |  |  | 2.5
2014-01-28 | Team meeting. Basic GUI design proposed. Began research on locking mechanism for github. |  |  |  | 3.1
2014-01-31 | Team meeting. Created high-level sketch of backend components. |  |  |  | 3
2014-02-01 | Reasearched deeper into the github locking mechanism. Found some alternatives, but nothing supported natively. Lock and key could be implemented. Not recommended. |  |  |  | 5
2014-02-03 | Team meeting. Discussed frontend design decisions. |  |  |  | 2
2014-02-04 | Team meeting. Client detailed more on the frontend GUI. Discussed a distribution system. |  |  |  | 1
2014-02-06 | Developed the back-end system more. Considered abstraction as primary importance. |  |  |  | 3
2014-02-07 | Team meeting. Proposed modular design plan. |  |  |  | 3
2014-02-08 | Further developed the modular design plan for backend. |  |  |  | 2
2014-02-13 | Discovered new requirements from client. Need to update backend accordingly. |  |  |  | 1
2014-02-15 | Updated the backend design as needed to reach client criteria. |  |  |  | 3
2014-02-18 | Team meeting. Received a rundown of the two pass compiler system from client. |  |  |  | 1
2014-02-21 | Began more detailed view of the backend structures, started looking into the deeper design and functional dependencies. |  |  |  | 6
2014-02-25 | Team meeting. Discussed project milestones with the client. |  |  |  | 2
2014-02-28 | Began working on flowcharts and functional dependencies in a more in depth graphical form. |  |  |  | 4
2014-03-03 | Team meeting. Discussed file flow from frontend to backend. Detailed the functional dependencies of the classes that make the backend. |  |  |  | 2
Date | Summary of Tasks Performed |  |  |  | Hours
2014-03-04 | Team meeting. Began discussing the official division of labor of the project. Began thinking about the detailed design in more final state. |  |  |  | 1.5
2014-03-06 | Team meeting. Further detailed the division of labor. |  |  |  | 3
2014-03-07 | Team meeting. Discussed coding standards. Detailed Design documents began being worked out. The official break down of the backend was proposed. |  |  |  | 3
2014-03-08 | Team meeting. Finalized the functional division of some of the components of the backend. |  |  |  | 3
2014-03-09 | Team meeting. Finalized the functional division of more parts of the backend. |  |  |  | 3
2014-03-11 | Team meeting. Finalized the data flow diagrams concerning the backend. |  |  |  | 3
2014-03-13 | Team meeting. Finalized the overall backend organizational structure. |  |  |  | 3
2014-03-14 | Team meeting. Began development of pseudocode for portions of the backend. |  |  |  | 3
2014-03-15 | Team meeting. Began development of pseudocode for portions of the backend. Began separation of the two halves of the backend, team assembler and team simulator. |  |  |  | 3
2014-03-17 | Began formulating plans to assist in the communication between the two halves of backend. Developed a system of interdependencies of programmers to assist with knowledge sharing. |  |  |  | 4
2014-03-18 | Team meeting. Improved upon portions of the backend. Proposed interdependency idea to group, agreed upon. |  |  |  | 3
2014-03-20 | Team meeting. Discussed checks and balances of the two halves of backend to ensure they were returning and accepting the appropriate variables. |  |  |  | 3.5
2014-03-25 | Drafted up initial plans for the integration of the back end pieces based off the information provided in the detailed design. Researched best way to implement errorDetection in the C# language. |  |  |  | 6
2014-03-27 | Created first draft of the errorDetection class. |  |  |  | 6
2014-03-28 | Problems implementing the errorDetection class over unit testing. Try catch block is not consistent with design document. Began working on redesign. |  |  |  | 4
2014-04-01 | Team meeting. Discussed shortcomings of the try catch block design of the errorDetection. Agreed to further research a method to implement that is in accordance to design. |  |  |  | 4
2014-04-03 | Team meeting. Finalized the functional requirements of the library class method requirements. |  |  |  | 2.5
2014-04-04 | Laid the framework for the library class into the project. Created the main driver function to access the methods of library. |  |  |  | 4
2014-04-05 | Team meeting. Created function to automate generation of addresses within the library class. |  |  |  | 4
2014-04-08 | Team meeting. Implemented an instruction to the library class of each of the instruction types to help with working without the team. |  |  |  | 4
2014-04-10 | Team meeting. Updated the documentation to reflect changes and to be in accordance with the coding standards. Implemented additional methods of the library class. |  |  |  | 4
2014-04-11 | Implemented additional methods of the library class. Modified existing functions to work with new abstractions introduced. |  |  |  | 4
2014-04-14 | Implemented the condition code clauses needed in the already existing methods of the library class. |  |  |  | 4
2014-04-15 | Finished implementing the condition code statements of the remaining methods in the library class. Further fleshed out the description portions of the headers to be correct with the coding standards |  |  |  | 6
2014-04-17 | Team meeting. Proposed a way to determine when the simulator should stop reading object code, decided on relying on a requirement for a final statement that all ASSIS/I programs used as an exit code. |  |  |  | 4.5
2014-04-18 | Updated code to have a reference to the frontend for updating the GUI elements corresponding to memory. |  |  |  | 3.5
2014-04-19 | Worked on a problematic function of the library class, XPRNT. |  |  |  | 3
2014-04-21 | Contacted artist for custom logo. Implemented final draft of the errorDetection class. Updated all code that could cause an exception to handle said exception. |  |  |  | 10.5
2014-04-22 | Team meeting. Attempted to integrate all available portions of the project to work with debug mode feature, incomplete. |  |  |  | 5
2014-04-23 | Updated the library accessor method to update the instruction trace needed for errorDetection |  |  |  | 3
2014-04-25 | Integrated front end updating on all methods that update main memory or registers. Integrated the errorDetections memory dump feature. Created online user manual html mockup. |  |  |  | 5
2014-04-26 | Team meeting. Began deep regression testing all function in library and errorDetection. |  |  |  | 7
2014-04-27 | Team meeting. Discussed further validation testing of the project as a whole. Updated the online user manual and the online help button of the GUI. |  |  |  | 7
2014-04-28 | Performed final changes on the code and began finalizing the presentation that is required to be presented. |  |  |  | 6
|  |  | Total Hours: | 194.6